## Appendix D-1 Preliminary Du (3) (hidden)
Question
Appendix D-1
Preliminary Due Diligence List
(Developmental Solar Resources)
2022 Request for Proposals
Renewable Resources
For Entergy Texas, Inc.
Entergy Services, LLC
October 10, 2022
Appendix D-1
PRELIMINARY Due Diligence LIST
Bidders intending to submit a proposal in the RFP must provide a comprehensive response to each question or request set forth in this document. Bidders should respond to any question or request that does not apply to the proposed Facility or transaction with “N/A” or “not applicable”. Bidders must respond to each question by 5:00 pm CPT on the Proposal Submission Deadline. Bidders are required to submit their response to the questions below in such a way that clearly identifies the question to which each response pertains, and then provide the response via PowerAdvocate to the Bid Event Coordinator. Additionally, Bidder should review the terms of the RFP, including Appendices B-1, B-2, C-1, and F, for technical specifications and other guidance or terms regarding the project.
Failure to submit a required response to a question or request in this Appendix D-1 may cause a Bidder’s proposal to be deemed non-conforming and rejected from further consideration. Failure to provide a comprehensive response could negatively affect a proposal’s evaluation. Bidders should keep in mind that the questions and requests in this document are not designed to inquire into or function as a survey of all requirements or elements of a proposed project or transaction, but instead seek material and information that ETI intends to use to assess the viability and specific aspects of proposed individual projects and transactions.
Project Overview
Provide a thorough executive summary of the proposal, including the project. The project summary should include, but not be limited to, the following: the proposed location, site description, (including the proposed routing of the project’s transmission lines), site control, technology, nameplate and guaranteed capacity of the proposed resource, design basis, plan for engineering/procurement/construction, proposed interconnection in MISO or SPP, MISO or SPP interconnection status, including current estimated costs for transmission interconnection, NRIS, ERIS (including, in each case, anticipated upgrades (including, without limitation, Network Upgrades, Standalone Network Upgrades, and Transmission Owner Network Upgrades) and improvements), and external NRIS (if applicable), estimated cost for transmission deliverability including NITS (if applicable), environmental compliance and permitting, financing plan, and non-standard project components/considerations. Anything provided in the summary should not otherwise limit Bidder’s response to any of the requirements below.
Please provide a list and summary of all power supply contracts or other off-take agreements that are currently in place or that are expected to be in place anytime in the future (including ancillary services).
Please provide a summary of the ownership or any joint ownership of the resource.
Confirm whether this project is part of a Package Bid
If so, describe in detail how the proposal would change, including bid price, if this project/resource/transaction were an individual proposal. This should include the drivers of the change, any corresponding price change, and the magnitude of any described impact.
Bidder Experience
Relevant Background.
Provide a detailed description of Bidder’s and all relevant Affiliates’ background and experience, including the key project team members, their relation to Bidder (e.g., employee of Bidder or Bidder parent), their backgrounds, development experience, and resumes. Confirm that key project team members, in the aggregate, have had direct responsibility for the development of at least three (3) completed utility-scale projects, regardless of generation technology.
Provide a list of sites where Bidder has developed, built, operated, and/or maintained at least one (1) utility-scale project with the generation technology included in Bidder’s proposal, including year(s) of installation, size, major equipment make and model information, and previous operational project successes and failures. Include details, such as project schedules, historical performance, and operating history.
Affiliates.
Provide a list of affiliated companies, including the proposed Seller (if different from Bidder), parent companies of Bidder, including the proposed Seller Parent Guarantor (as referenced in Appendix F and the Bidder Registration Form), holding subsidiaries, and predecessor companies.
Project Development
RFP Review
Confirm that Bidder has reviewed and is familiar with the terms of the RFP, including the Model BOT Agreement and the Scope Book (for BOT proposals), the Model PPA, including Attachment B-1 (for PPA proposals), and Appendix F (Credit/Collateral Requirement).
BOT Only - Provide a complete redline version of both the Model BOT Agreement and the Scope Book showing all Bidder exceptions to the terms and requirements of either document.
PPAs Only - Provide a complete redline version of the Model PPA showing all Bidder exceptions to its terms.
Provide an issues list organizing and summarizing Bidder’s special exceptions. The issues list should be consistent with the redline versions of the Definitive Agreement submitted in the Proposal Package, include Bidder’s alternative positions on each identified issue, and note the relevant contract section(s) covered by the issue.
Engineering
Provide the most recent preliminary design study performed for the proposed resource, including the BESS option, if proposed.
Provide the most recent detailed engineering study performed for the proposed resource, including the BESS option, if proposed.
Provide the most recent project site plan, one-line diagram, Solar PVSyst Model, and Solar PVSyst Report. The Solar PVSyst Model (including native .prj, .met, .ond, and .pan files) and Solar PVSyst Report provided should meet the requirements specified in the Scope Book.
Safety
Provide a copy of Bidder’s corporate safety and security policies applicable to the project and the work, (or that are expected to serve as the basis for Bidder’s safety and security programs and policies for the project and the work), including safety and security policies utilized at project sites.
Provide safety metrics for the last three (3) years, plus current metrics, for Bidder’s and any of Bidder’s proposed or expected prime contractors and subcontractors, including, without limitation, total recordable incident rate (TRIR), days away restricted or transferred (DART), OSHA willful or serious citations, near-miss incidents, fatalities, number of years in business, etc.
Is Bidder a registered participant in the Avetta (www.avetta.com) or a comparable third party risk management compliance tracking network or system? If so, please describe the risk management compliance tracking network or system in which Bidder is a registered participant.
Project Schedule
Provide a Level 1 schedule that includes major milestone events and critical activities and associated estimated dates to achieve the successful completion of the project. For purposes of the Level 1 schedule, assume that Buyer’s regulatory approval is received by the date for such approval indicated in Section 4.1.1 of the Main Body (as may be updated from time to time, as noted therein). If a BESS option has been proposed, include those activities in the Project Schedule. Milestones that should be addressed in the schedule include, but are not limited to, the following:
Note: Items marked by an asterisk “*” are required to be included or specifically addressed in any Definitive Agreement.
Receipt of major permits (include permitting activities);*
Execution of major project contracts (e.g., MISO or SPP Generator Interconnection Agreement and related interconnection or deliverability contracts, prime EPC contract, site purchase/ lease/ easements/ rights-of-way);*
Proposed Full Notice to Proceed (“FNTP”) Expiration Date (BOT proposals) or deadline for receipt of Buyer’s Required Governmental Approvals (PPA Proposals);*
Project construction financial closing (if applicable);
Site Mobilization Date;
Delivery of major equipment;
Installation of substation and interconnection equipment (which, for BOT proposals, is required to occur before energization and synchronization of the proposed resource to the host electric grid);
Estimated Standalone Network Upgrade completion date;
Estimated Transmission Owner’s Interconnection Facilities completion date;
Estimated Network Upgrade completion date;
EPC contract procurement (if applicable);
Major equipment procurement dates;
Expected Mechanical Completion date (BOT proposals only);*
Expected Closing Date (BOT proposals only);*
Expected date when the resource will be placed in service for federal tax purposes;
Expected Substantial Completion Date (BOT proposals) or Delivery Term Commencement Date (PPA Proposals);*
Guaranteed Substantial Completion Date (bearing in mind the Change Order terms of the Model BOT Agreement and highlighted in Section 2.1 of the Main Body (BOT proposals)) or Guaranteed Commercial Operation Date (PPA Proposals);*
Proposed Substantial Completion Termination Trigger Date (BOT proposals only);*
Expected Final Completion (BOT proposals only);* and
Proposed Final Completion Termination Trigger Date (BOT proposals only).*
If available, provide a detailed construction schedule.
Provide a date (which must be at or prior to the proposed Closing Date (BOT proposals only) or proposed Guaranteed Commercial Operation Date (PPA proposals only) by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Closing Date (BOT proposals only) or Guaranteed Commercial Operation Date (PPA proposals only).
For BOT projects that have started construction, confirm that Bidder understands that a project in-service date not satisfying the IRS continuity safe harbor as provided under IRS Notice 2013-60 and IRS Notice 2018-59, as amended may jeopardize the receipt of the guaranteed ITC or PTC associated with the proposed project and may result in Seller being responsible for the lost tax credit.
State the number of days of “float,” to accommodate schedule delays, between the expected Substantial Completion Date and December 30 of the year of the Guaranteed Substantial Completion (BOT proposals only).
Insurance
Confirm the level of insurance coverage that will be included in the project for the following:
Worker’s compensation
Business auto liability
Comprehensive general liability
Errors and omissions
Equipment
Excess liability insurance
Builder’s all risk insurance
Project Cost Estimate
Provide the accuracy of the project cost estimate using an appropriate cost estimate classification system (e.g., Class 1 through Class 5) for both the Solar PV resource and the BESS option, if applicable.
Note: Proposal project cost estimate should be based on front-end engineering from a qualified external and/or internal source that supports at least a Class 3 (as defined by AACE standards) cost estimate (-20% to +30%).
Describe how the estimate(s) were developed (e.g., third-party engineering firm, inhouse, vendor supplied bids, etc.).
BOT Only - Complete and provide Appendix D - Attachment A-1 (Solar BOT Cost Components), which is included in the RFP documents.
PPA Only - Complete and provide Appendix D - Attachment A-2 (Solar PPA Cost Components), which is included in the RFP documents.
Site Control and Assessment
List the real estate and related facilities and real property interests, both owned and leased, with legal description(s), required for development, ownership, use, and/or operation of the resource.
List all easements, rights-of-way, servitudes, and other land or facility use agreements entered into or required to secure the ability to design, engineer, construct, own, use, and/or operate and maintain the proposed Facility and associated infrastructure.
Provide an unredacted copy of Bidder’s, Seller’s, or an Affiliate’s proof of ownership of, a legally binding lease of, or a legally binding option or comparable agreement to purchase, lease, or similarly control the site of the proposed resource or any portion thereof.
If the proposed project site or any portion thereof is under a lease, lease option, or similar site control agreement, identify the term of each lease agreement, lease option, or similar site control agreement, including dates. If there is a lease option, indicate whether the option includes any option extension rights and the consideration/ payment(s) required for each such extension.
If the proposed project site or any portion thereof is under a lease, lease option, or similar site control agreement, identify when it was executed and the length of the development period permitted under the agreement. Does the development period include allowance for construction of the Facility? Please provide the consideration/ payment(s) required by the agreement over the development period, according to payment type.
If the project site is secured in whole or in part under a purchase, lease, or similar option, when does the option expire and when will the option be exercised? State whether the option includes any option extension rights and the consideration/ payment required for each such extension.
Provide the acreage secured under each site purchase, lease, or option agreement, the total expected acreage of the project site, and the total expected acreage of the completed project.
Provide a site map indicating the expected boundary of the full project site, indicating which parcels are currently under Bidder’s control and which are not.
Provide evidence that the project site is properly zoned for the project and the use contemplated by the RFP.
For any parcel not currently under Bidder’s control, indicate whether Bidder is actively negotiating with the landowner (or agent or representative thereof) and, if so, the expected timeframe which Bidder expects to execute agreement(s) with the landowner(s).
Confirm that site control of the project site (or the portions under Bidder’s or Seller’s control), including appurtenant easements benefitting the project, could be extended if the term plus the extension option(s) is for a period less than 40 years. If it is less than 40 years, explain the options to pursue a longer term or additional extension option(s).
Provide an executive summary of any formal reports or studies (whether internally or externally prepared or both) related to the risk assessments of the project site, including, without limitation, any risk assessments related to environmental, ecological, archeological, soils, subsurface, geological, hydrogeological, or other site conditions, meteorological conditions, flooding, fire, prior use, habitat, wildlife, or mineral interest or other burdens on title or use that may render the site unusable or delay or otherwise impair or adversely affect project development or use.
If the site has not been formally assessed for the risks included above, what supporting facts or actions provide assurance that the site is fit for the intended use?
Indicate what construction-related surveying or testing has been performed at the site and summarize the results or provide executive summaries related to the surveying or testing.
Is the proposed project site within a floodplain or area subject to storm surge? If so, identify the designated zone and the corresponding level of exposure.
Are any easements or variances required for the site or ownership or use of the Facility? If so, briefly describe the needed easement(s) or variance(s) and explain why they are needed.
Is the site located in or near wildfire-susceptible or wildfire-prone areas? If so, please provide the estimated distance from the project site to the nearest edge of each wildfire-susceptible or wildfire-prone area.
If the proposed project site is near wildfire-susceptible or wildfire-prone areas, provide a description how Bidder plans to mitigate potential risks these areas present to the project, and plans to minimize impacts of any facility fires on forestry, woodlands, grasslands, wildlife, and surrounding property.
Is the proposed project site subject to windstorms (50-year peak gust) greater than 40 m/s (90 MPH)? If so, provide details of panel fastening system.
Describe the status of any necessary site infrastructure, including, but not limited to:
Transportation/road access for construction activities and ongoing operations; and
Lay down area access for construction.
Provide the following details regarding the proposed project site:
A description of the exact location (i.e., street address or latitude and longitude if in a rural location);
A property plat, if available;
Useable acreage required for project size offered;
Other available acreage adjacent to the site; and
Nearby acreage directly or indirectly under Bidder’s or Seller’s control.
The land’s primary use(s) over the five years preceding the response to this request (e.g., timber harvesting/forestry, sugar cane production, rice production, farming (noting principal crops), grazing, vacant lot, etc.).
Provide the following documentation for the proposed site:
Title insurance commitments or policies covering all or any portion of the real property (including appurtenant easements) comprising the proposed site;
ALTA surveys, referencing the above title commitments if available, covering all real property (including appurtenant easements) comprising the proposed site, showing all existing improvements and site features, access to nearest public roads, and plotting all plottable exceptions listed on such title commitments (or noting that such exceptions are either unplottable or do not affect the site);
Copies of the vesting instruments for the proposed site (including appurtenant easements), and all documents listed as exceptions in such title commitments or surveys;
Copies of real property tax documentation; and
Other available real property documentation.
Facility and Equipment
Describe the proposed Facility and equipment to be utilized in as much detail as is reasonably available.
Provide an equipment list for other equipment to be utilized at the site.
Provide the rationale for the selection of the major equipment to be incorporated into the Facility.
Discuss the viability of the proposed technology, the operational reliability, and the experience, industry standing, and creditworthiness of the manufacturers of the major equipment.
Discuss the warranties for the major components of the project.
Discuss and provide published reports demonstrating that the proposed technology (including, if offered by Bidder as an option in its proposal, the BESS) for the Facility and related infrastructure is commercially proven.
Describe the plan or Bidder/manufacturer requirements and/or expectations for operation and maintenance of the Facility, including prior to the Closing, during commissioning and testing, and after the Closing (BOT proposals) or the Delivery Term Commencement Date (PPA proposals). (If Bidder is offering a BOT proposal, review the relevant provisions of the Model BOT Agreement and the Model Scope Book before answering. If Bidder is offering a PPA proposal, review the relevant provisions of the Model Solar PPA, including Attachment B-1 before answering.)
Provide proposed Project Performance Testing (Capacity and Availability) procedures. The procedures are expected to include, among other things, pre-test meetings, checks, and other requirements, test procedures and protocols, notice and engineering, equipment, instrumentation, monitoring, control system and other document deliverables, and data collection and filtering.
Provide the type and model of the on-line monitoring system and multi-gas monitoring system for the project’s transformer.
Describe how the requirement for ASCE-7, Risk Category III design wind speed will affect choice of tracker systems and other structural components.
Operational Characteristics
Confirm that a solar irradiance study has been performed for the proposed site and the results of such study were used and reflected in the Energy Model/PVsyst report provided to Buyer as part of the Proposal Package. If Bidder confirms, specify the data source, the length/duration of the data made available by the data source, and explain the results and how they support the projected annual generation.
Provide an expected hourly generation profile of the Facility by completing Appendix D - Attachment B (Hourly Profiles). The generation profile should be for at least two (2) years using the most recent data and based on data at or in close proximity to the site of the proposed resource. Provide both P50 and P90 for solar only and solar-with-BESS configurations separately, if applicable. Onsite measurement data is preferred.
Explain the source of information for the hourly generation profile supplied in Attachment B, the resource data measurement methods used, the assumptions for any equipment (including transformers)/transmission/etc. losses, the location(s) where the data was measured, and the means of obtaining the data, including instrumentation type(s) and associated testing tolerances.
Did an unaffiliated third-party subject matter expert prepare the reports associated with the data and/or the profile? If so, identify the SME(s) and the scope of their engagement.
Describe the risks of basing the generation calculations on the data.
Describe the technical challenges relative to the project’s scale, such as manufacturing capacity of supplier production, complexity of deployment and sequencing processes, vendor backlog, supply, materials, or labor shortages, etc.
If Bidder is offering a PPA proposal, provide the Annual Expected Energy Quantity (AEEQ) and Annual Guaranteed Energy Quantity (AGEQ) for the Facility by completing Appendix D - Attachment D (Annual Energy Quantities).
Contract Status
Provide a project team and contractor/sub-contractor organization chart.
List and describe the licenses and other authorizations required for Bidder/Seller to undertake and complete the project or perform the associated work under applicable rules, regulations, and other laws, including (if applicable), without limitation, any required solar classification license, and Bidder’s plan for ensuring such licenses are obtained.
Describe the procurement and contracting plans for the project, including:
Procurement plan and status for each of the PV modules, including the Solar PV panels, power conversion units (or inverters), generator step-up transformer, and trackers;
Procurement plan and status for the other major equipment;
Procurement plan and status for design engineering;
Procurement plan and status for permitting support;
Procurement plan and status for the EPC contract, if applicable;
When is such an EPC contract expected to be executed?
Is there a letter of intent in place with an EPC provider?
If no such letter of intent is in place, have proposals been requested from possible EPC providers?
If Bidder does not intend to use a traditional EPC contract for the facility, please provide the following information and answer the following questions:
Describe contracting methodology.
Are contracts in place for construction/construction management?
When is this activity expected to be completed?
Are there letters of intent in place with such providers?
If no such letters of intent are in place, have proposals been requested from providers of construction/construction management services?
Procurement plan and status for the site management contract, if applicable; and
Procurement plant and status for other material project goods and services.
Impacts of Auxin Solar anticircumvention case
Describe the likely effects on the project in terms of time and cost for completion of the Auxin Solar anticircumvention case and identify the current suppliers of solar panels to the project and the extent to which they are subject to the case.
Describe your procurement plan, if any, with respect to acquiring solar panels from sources not covered by the Auxin Solar anticircumvention case to mitigate these risks.
If applicable, share any information you have collected from your solar panel suppliers concerning the arguments and facts they will present in response to the Department of Commerce to try to exclude themselves from the case or to argue for a low individual rate of AD and CVD duties.
Share any information concerning the historical AD and CVD rates of these suppliers with respect to solar panels exported from China to provide a range of potential exposure if the Department of Commerce rejects their arguments and requires a cash deposit of estimated AD and CVD duties following a preliminary affirmative determination.
Did the executive announcement of 6/6/22, reflecting a 24 month period without tariffs imposed, affect your proposal/panel procurement plan? If so, describe that plan and confirm whether the impact of the executive order is incorporated with the proposal submitted.
Is the project based on a firm proposal as bid, including both cost and project schedule, taking into account the implications of the Auxin Solar anticircumvention case?
If the proposal is not firm, propose a price and/or schedule provisions to be included within any resulting contract to account for bidder’s uncertainty.
If a tariff were to be implemented following the Auxin Solar anticircumvention case, would there be an impact to the proposal?
If there is an impact, describe how the price or schedule would change.
If there is no impact, please provide rationale supporting no impact.
If a revised firm price would result from the Auxin Solar anticircumvention case, due, in part, to selection of a different module manufacturer, provide updated performance estimates including annual energy quantities, degradation, year 1 hourly profile data, and PVsyst report or other applicable documents supporting any changes.
Is the Bidder’s project schedule contingent on an assumed timeline for the Auxin Solar anticircumvention case? If so, what is the assumed timeline, and what are the implications if the DoC does not meet the assumed dates?
Battery Energy Storage System (“BESS”) (if applicable)
Provide the size of the proposed BESS (capacity and duration) and indicate whether it will be AC or DC-interconnected.
Provide the expected annual degradation rate for the storage capacity of the proposed battery and the assumptions underlying such expected degradation rate.
Provide the power rating of the proposed BESS.
How many strings in the proposed project will have batteries connected to them and how many will not?
Does the BESS for the proposed project have expansion potential within the enclosure(s)? If so, how much?
Does the BESS solution require augmentation in order to achieve its design life? If yes, describe the augmentation plan.
Provide the proposed BESS manufacturer information for the project.
Provide a Preliminary Fire Risk Analysis for the proposed BESS, including, but not limited to, the following:
Comparison of the features of the proposed BESS to the requirements listed in NFPA 855 and confirm the BESS is certified UL9540 and UL9540A compliant
Basis for physical separation of multiple BESS units from each other and from other site structures and equipment to protect against uncontrolled fire spread;
Proposed means of protection against fire effects due to thermal runaway; and
Proposed means of protection for site personnel, including fire responders, from the effects of deflagration/explosion energies in the event of uncontrolled thermal runaway.
Provide the technical details of the proposed BESS, including, but not limited to, the following:
The maximum depth-of-discharge for the BESS;
The round-trip efficiency rating for the proposed BESS, the expected annual degradation rate related to round-trip efficiency, and the assumptions underlying such expected degradation rate;
The proposed life of the BESS under standard operating conditions;
Relevant specifics of the manufacturer warranty offered on the proposed BESS, including, but not limited to, cycles, years, capacity, restrictions, etc. as presented by the manufacturer; and
The ancillary services (e.g., grid support services such as voltage support) the BESS is capable of providing.
Provide the number of installations worldwide (by projects and in MW) of the proposed battery technology (separate out developmental projects and those in commercial operation).
Does the project’s MISO Interconnection Application include ERIS and NRIS (if applicable) for the inclusion of the BESS with the proposed solar project? If it does not and the proposed project including the BESS is selected, describe Bidder’s plan to update the MISO Interconnection Application or the GIA (as applicable) for the project and to reflect inclusion of the BESS in the project, including the timing of the update and the expected schedule for completion of any studies or material analysis performed by MISO in connection with the update.
Confirm that the following principles regarding data collection and use from the Battery Management System (BMS) or other BESS system are acceptable to Bidder and/or the BESS vendor: The data collected from the BMS or other BESS system will be owned exclusively by Buyer and under Buyer’s sole control. Buyer will make available to Seller a finite set of data from the BMS or other system necessary for continued warranty support by the BESS vendor. All other access to and use of such data and the BESS will be strictly limited. If Bidder is unable to confirm as requested, state the specific reasons why confirmation cannot be provided.
What data, if any, will Seller and/or BESS vendor expect to collect in connection with the proposed BESS for the project? List all data elements.
For each data element, state how the collection and use of data is directly relevant to Seller’s performance of the scope of work for the proposed project.
If Bidder is unable to confirm the acceptability of the data-related principles outlined in item 3.11.12, describe in detail all the desired uses of any data expected to be collected, including any use involving marketing, data monetization of any kind in any form, product development, incremental service offerings, analysis, or sharing of all or any portion of such data (or information derived therefrom), and the need or justification for such use.
Provide a list of any third parties, including parent company, Affiliates, and hosting providers, that will have access to data collected from or by the BMS or other BESS system and Bidder’s purpose for sharing such data.
Describe how Bidder intends to protect the confidentiality and security of data collected under the proposed project. If Bidder intends to share data with third parties, what confidentiality requirements and use restrictions will apply to such third parties regarding such data?
If data will or may be hosted by Seller or vendors, provide a copy of the SOC 2 Type 2 report or similar audit report for the applicable facilities.
Supplier Diversity in Contracting
Attach Bidder’s or its Affiliate’s supplier diversity policies and practices with respect to project contractors, suppliers, and the performance of contracted work.
Confirm that Bidder plans to apply these practices and policies to the proposed resource/project. If Bidder does not have a supplier diversity policy or will follow a different procurement and contracting strategy for the proposed resource, describe in detail the measures that will be taken during development, engineering, procurement, construction and other activities related to the resource to ensure diverse contracting practices are followed.
If available, provide the project target levels for the following business categories for the proposed project in relation to the corporate policies and practices (expressed in percentage targets and overall project spend, and percentage of subcontracting spend):
Veteran-owned businesses;
Service Disabled veteran-owned businesses;
Women-owned business enterprises (WBEs);
Minority-owned businesses;
LGBT-owned businesses;
Small business operating in a HUBZone; and
Others, identified by Bidder’s or its Affiliate’s contract procurement practices or policies.
Indicate the percentage of contracting and subcontracting spend (contracting and subcontracting spend excludes OEM spend and, for clarity, EPC spend that is self-performed) for the proposed project which will be intended for utilizing diverse contracting practices.
Confirm that in the Definitive Agreement Seller will commit to comply with the contracting plan for the retention of, and a target Addressable Spend (as defined in Appendix H) for, diverse and local suppliers.
Electric Interconnection & Transmission (MISO)
Transmission Interconnection and Full Deliverability
Provide a complete copy of the submitted interconnection application(s) for the proposed Facility (including, without limitation, the quantity of NRIS, ERIS, and external NRIS, required by the RFP), a copy of either the letter acknowledging the application or, if available, the actual study results related to such application.
If available, provide a copy of the generator interconnection agreement and any and all related or similar agreements for the resource that have been executed or are material for the resource’s interconnection, deliverability, or transmission capabilities.
If available, provide the interconnection and transmission costs for the proposed Facility and a description of each associated upgrade or improvement; otherwise, provide:
The phase of the MISO DPP cycle the resource occupies at the time of proposal submission;
The interconnection and transmission costs and associated upgrades or improvements that have been identified and/or estimated by MISO with respect to the interconnection application (inclusive of any request for both ERIS, NRIS, external NRIS and any other required deliverability service for the proposed Facility) for the proposed Facility;
The interconnection and transmission costs and associated upgrades or improvements that have been identified and/or estimated by Bidder for the proposed Facility, and if different from the MISO estimate, the reason(s) for the difference(s); and
The interconnection and transmission costs for the proposed Facility included in the proposal pricing.
Include in the response(s) to item 4.1.3 above a breakdown of the actual (if available) or estimated (if not) transmission owner interconnection facilities costs, standalone network upgrade costs, network upgrade costs, affected system upgrades, applicable transmission service upgrades, and any other material interconnection and transmission costs.
Include in the response(s) to item 4.1.3 above the estimated timeframe for completion of each estimated upgrade.
Confirm that the interconnection and transmission costs included in Bidder’s proposed purchase are adequate, in Bidder’s judgment and experience, for the costs and risks associated with the interconnection, deliverability, and transmission interconnection and transmission cost estimates in the proposal pricing and state the basis for that opinion including supporting data and material.
Confirm that Bidder has agreed to accept the risk that the final interconnection and transmission costs may exceed the costs included in the proposal pricing and that the interconnection and transmission upgrades may be completed later (or earlier) than scheduled or expected.
If not included in a response above under item 3.7 above (Site Control and Assessment), provide any available information or Bidder’s plan regarding land options, land purchase agreements, permits, etc. required to complete the installation of or to use the interconnection facilities (e.g., transmission line rights-of-way).
Identify any public or private road, water, land, or other similar crossing required or potentially required for the project to be able to transmit power to the point of change of ownership of the transmission facilities associated with the project and, for each such crossing (other than those on land owned by Seller) and each affected property, identify the expected means and related material details of effectuating the crossing (e.g., buried/underground lines, with expected burial depths, encasements, etc.) and the schedule for obtaining the necessary consents or permissions for the crossing, and, for BOT proposals, confirm that Seller does not intend to rely on Buyer’s power of eminent domain to procure such consents or permissions.
Environmental
Please list any potential environmental impediments to project development, provide documentation and describe the plan to mitigate the impediment.
Land/Groundwater
Have the previous land uses for the proposed resource/site been identified? If so, list those uses and provide the supporting information.
Have any potentially contaminating activities at or nearby facilities/sites been identified? If so, list and describe those identified.
Has an environmental impact study been conducted for the resource/site? If so, provide a copy of the study(ies). (See also item 3.7.10 above)
If applicable, provide the number of groundwater monitoring or production wells at the Facility/site and provide copies of state registrations for each well.
Does Bidder possess or is Bidder aware of documentation or material identifying or concerning the details of the geological and hydrogeological nature of the soil and groundwater underneath the resource/site? If so, provide (if Bidder possesses or can reasonably obtain) or direct Buyer to the source of (if Bidder does not possess or cannot reasonably obtain) such documentation or material. (See also item 3.7.10 above)
Has a wetlands survey been completed for the proposed project site? Have any potential wetlands been identified on the property? Provide a copy of any completed wetlands surveys of the property (including desktop reviews and on-site surveys). (See also item 3.7.10 above)
Has the site been evaluated to determine if it is located in a flood hazard area? If so, identify the FEMA flood zone, the corresponding level of exposure and provide a copy of the study.
If the site is within a 100-year floodplain or flood prone area, provide a detailed flood mitigation plan.
Permitting
Provide a list of all environmental, construction, and operation permits required for the project, including permits needed to develop, design, engineer, build, test, commission, own, use, operate, or maintain the project. Provide a copy of any permits received for the project to date.
Provide evidence that Bidder has completed all permitting due diligence necessary to prepare to apply for all required permits (e.g., a copy of the draft permit application(s) or a summary of the permit application requirements, including how those requirements will be met).
Provide a “Phase I” environmental site assessment according to ASTM E1527 or evidence and documentation of due diligence specific to the proposed site necessary and sufficient to support such an assessment (e.g., documentation of work necessary to meet the primary components required under a Phase I according to ASTM E1527).
Describe any reasonably anticipated permitting obstacles for the proposed project and any pending claims, actions, or disputes related to permitting activities undertaken to date.
Has Bidder contacted or otherwise been in communication, directly or indirectly, with any of the local governing bodies regarding the proposed project? If so, for each such governing body, indicate whether it has expressed opposition to or support of the project and briefly summarize its position.
Were any de minimis conditions identified in the project site assessments? If so, describe the condition and any expected effect on the project development or schedule.
Noise / Federal Aviation Administration / Department of Defense / Avian / Wetlands / Archeological/Historical Preservation / Protected and Endangered Species
Have the requirements for the project site or the Facility to comply with applicable noise, Federal Aviation Administration, Department of Defense, avian, wetlands, archeological, historical preservation, protected species, and endangered species rules, regulations, and laws been determined and assessed? If so, state any special concerns or limitations and note whether any regulatory compliance activity has been undertaken by or for the project owner or any Affiliate or submitted to any governmental agency.
Provide a list of all federally protected wildlife with schedule for obtaining any permits required to operate the develop and operate the Facility.
Provide a list of all species not considered federally protected, but are considered to be on the watch list to become endangered or federally protected in within the next 5-years?
Provide the date by which the Bidder guarantees receipt of all permits required to develop and operate the Facility.
If applicable, what are the anticipated or current controls for noise?
For each parcel forming the project site, identify the location of the nearest residence.
For each parcel forming the project site, identify the location of the nearest business.
Environmental Compliance
To the best of Bidder’s knowledge, has the proposed project or the project site been the subject of any complaints or criticism from or concerns expressed by governmental authorities, citizens or citizen groups, business or commercial organizations, or local media regarding environmental matters (including, without limitation, noise, traffic, dust, fishkill, birdkill, riparian matters, planned usage complaints, “Not in My Backyard” complaints, and complaints from nature/sports/ recreation enthusiasts/advocates) or adverse commercial effects?
Does Bidder/Seller/parent/project owner have (i) an environmental policy or statement of environmental commitment and (ii) an environmental management system that would or may apply to the proposed project or the project site? If so, provide a copy of the policy(ies).
List any identified known or potential environmental impediments to project development, provide any associated documentation, and describe the plan to mitigate the impediments.
Has an assessment been made to determine if any material capital expenditures or material expenses need to be incurred to comply with any existing or proposed (whether in preliminary or final form) environmental regulations? If so, describe the assessment and its results.
Environmental Sustainability
Describe how Bidder plans to design and manage the project site and any appurtenant easements during design and construction, including minimizing environmental and vegetation impacts associated with the proposed solar facility. Include descriptions for planned practices, such as the enhancement of pollinator habitat through use of low-growing native seed mixes, natural ground covers, and natural hedges. (For BOT transactions, the description should be through the substantial completion payment date or, if O&M services are offered as part of the proposal, the expiration of the term of the services offered.)
Does Bidder comply with the NREL/NSF Standard 457 regarding Sustainability Leadership for PV modules?
Do the modules proposed for the resource contain per- and polyfluoroalkyl substances (“PFAS”), including PFOA, PFOS, GenX, and other similar compounds? If yes, provide additional details regarding the chemical contents of the proposed panels.
Are the modules proposed for the resource manufactured via processes that utilize PFAS?
Community Outreach
Provide Bidder’s plan for community outreach.
Provide a summary of Bidder’s actions to date with regards to community outreach and/or communication with nearby businesses and residences.
Provide documentation of any community support or opposition for the proposed project.
Project Structure and Finance, Credit, Taxes, and Accounting
Ownership Structure. Provide a detailed description and organizational chart of the ownership structure for the proposed project prior to the Closing (BOT transactions) or the Delivery Term start date (PPA transactions) and for at least three (3) years after the Closing or the Delivery Term start date, as applicable.
Financing Plan. Provide a reasonably detailed summary of Bidder’s plan for structuring and financing the proposed project and funding the financing, including the sources of debt and equity and, for BOT transactions, whether Seller intends to use balance sheet financing (i.e., self-finance the project using Seller and/or Affiliate funds) or unaffiliated third-party financing?
Successful Financings; Financing Discussions. Provide evidence of at least one (1) recent successful financing completed by Bidder (or an Affiliate) or that potential lenders or investors (including tax equity investors) have been engaged in initial, bona fide discussions to ascertain interest, market conditions, and indicative terms for financing the resource.
Nominated Seller Parent Guarantor. After reviewing Appendix E to the RFP, specify whether Bidder’s proposal includes the provision of a Seller Parent Guaranty and, if it does, confirm that the entity that Bidder proposes as the Seller Parent Guarantor (including, without limitation, as a financial co-signer) in respect of any Definitive Agreement and any related agreements with or commitments to Buyer is the entity identified as the Seller Parent Guarantor in the submitted Bidder Registration Form for the proposal. If Bidder is proposing a different entity as the Seller Parent Guarantor than the one identified in the Bidder Registration form or otherwise in the Bidder Registration Process, specify the entity proposed as the Seller Parent Guarantor.
Securitization Plan.
Provide Bidder’s/Seller’s plan for meeting the credit/collateral requirements outlined in Appendix F (review that appendix thoroughly before answering).
Confirm that Bidder’s proposal and plan satisfy the requirements of Appendix F.
Provide the credit certification required by and described in Appendix F and Section 5.1.6 of the Main Body (a form of which is provided in the RFP documents titled Appendix D - Attachment F), signed by a Treasury Officer (as defined in Section 5.1.6 of the Main Body).
Collateral Form. Without limiting item 6.5 above, if Bidder is proposing a BOT transaction, describe the form of collateralization (letter of credit, cash holdback, or combination of both) that Seller or Seller Parent Guarantor will utilize during the period from the Closing through the release of post-Closing credit support (see Section B of Appendix F), including, if a blend will be used, the percentage that will come via letter of credit and the percentage from cash holdback at the Closing, the Substantial Completion Payment Date, and other credit adjustment milestones (which must total to 100% of its post-Closing liquid credit support obligation and comport with the requirements of Appendix F).
Certain Financing Documents. List any actual or expected (i) resource-specific debt instruments, (ii) credit agreements, indentures, letters of credit, reimbursement agreements, guarantees, indemnities, or assumption agreements and agreements relating to contingent obligations and any amendments thereto, (iii) security or pledge agreements, or (iv) agreements or instruments evidencing a lien or encumbrance on or other right with respect to any of the assets of the resource, relevant, in each case, to financing the proposed project or evaluations of Seller’s or Seller Parent Guarantor’s creditworthiness or the proposed BOT acquisition transaction.
Financial Statements. Provide, in PDF form, the current pro forma financial statements for the proposed project, the audited financial statements for Seller and/or Bidder’s proposed Seller Parent Guarantor for the most recent two (2) years, and the current-year reviewed quarterly financial statements, including the auditor’s opinion and notes to the financial statements, the balance sheet, the income statement, and the cash flow statement (indicating which of the following are being submitted: 10-Ks; 8-Ks; 10-Qs; and Other (describe)), along with the long-term debt structure and lien information that might affect the creditworthiness of Bidder and/or its Seller Parent Guarantor. To the extent the foregoing information was requested and provided as part of the Bidder Registration Process, Bidder may note this fact in its response and provide only the material and information not previously provided. If financial information is consolidated with other entities, the data related to Seller or Seller Parent Guarantor must be extracted and submitted as separate documents by Bidder.
Seller/Seller Parent Guarantor Information. The proposal must include the information requested in items 6.9.1 through 6.9.7 below for Seller and any entity that Bidder proposes as a Seller Parent Guarantor in respect of any Definitive Agreement. To the extent any of the foregoing information was requested and provided as part of the Bidder Registration Process, Bidder may note this fact in its response and provide only the material and information not previously provided.
Type of Business
Corporation, Limited Liability Company, Partnership, Other (describe)
Organization
Legal Corporate Name
Street Address
City, State, Zip Code
Dun & Bradstreet Number
Federal Tax ID Number
Beneficial Ownership
List of Executives and Directors
Credit Contact
Name
Title
Phone Number
Email Address
For Corporations/Limited Liability Companies
Date and State of Incorporation/Registration
Street Address
City, State, Zip Code
For General Partnerships
Name of General Partner
Address of General Partner/Registered Agent
City, State, Zip Code
For Others, similar relevant information
Most recent credit rating (if any), as determined by Moody’s, S&P, and/or Fitch.
Pending Claims. List any pending claims, actions, disputes, or other proceedings currently pending or threatened against the project.
Bankruptcy. Provide copies of all relevant, material bankruptcy court filings or orders, including any order discharging Bidder, Seller, and/or the proposed Seller Parent Guarantor from the bankruptcy proceedings and any order that could reasonably be expected to adversely affect the proposed project or credit support for Seller’s obligations with respect to the project.
Tax Abatement and Mitigation. Provide any tax abatement, tax reduction, tax deferral, tax mitigation, or similar agreement or arrangement executed by or on behalf of Bidder/Seller or any Affiliate with any federal, state, or local authority or other third party with respect to or affecting the project or the project site, including all amendments to any such agreement and any equipment or services related to the project or the project site. If no such agreement is in place, identify and describe any proposed tax abatement, tax reduction, tax deferral, tax mitigation, or similar arrangement proposed for the project or assumed in the proposed purchase price.
Property Tax Protests. Provide relevant documents related to any formal or informal property tax protests, litigation filed, related correspondence, legal opinions received, and judicial or administrative decisions rendered during the last ten years and year-to-date, and current status of any such proceedings with respect to the project site or the project.
Property Tax Agreements. Provide copies of any formal or informal property tax agreements (i.e., PILOT, TIP, etc.) with state or local authorities in force during the preceding five years or effective in the current year or succeeding years with respect to the project site or the project.
Tax Jurisdictions. List all applicable tax jurisdictions, tax rates, millage rates, assessment ratios, and the current equalization ratio.
Available Tax Benefits. Describe any other awards, grants, incentives, special tax treatment or credits (excluding the federal investment tax credit or production tax credits for solar-powered generation facilities established pursuant to Section 48, Section 48E, Section 45, Section 45Yof the U.S. Internal Revenue Code (“ITC” or “PTC”)), tax abatements (see Section 6.17 for Property Tax Abatements), tax reductions, incentives, or subsidies that are or may be available to the proposed resource or project. Describe the same, identify any applicable critical schedule deadlines, and indicate the anticipated likelihood of Bidder/Seller and/or the proposed resource receiving the same.
Property Tax Abatements. If you answered “yes" to the Property Tax Abatements question in row 41 of the Proposal Submission Template, please provide critical schedule deadlines and indicate the anticipated likelihood of Bidder/Seller and/or the proposed resource receiving the specified property tax abatements.
Effects if Tax Benefits Not Received. Identify the economic and other effects on the proposed resource or project in the event that any applicable award, grant, incentive, special tax treatment or credit (excluding the ITC or PTC), abatement, reduction, or subsidy is not received.
ITC/PTC.
Provide the ITC percentage and the PTC level ($/MWh, first year) for the proposed project (and reflected in your proposal). If the proposal offers only an ITC or only PTCs for the proposed project, specify the ITC percentage or the PTC level ($/MWh, first year), as applicable, and the rationale for limiting the proposal to offering only an ITC or PTCs, as applicable.
If the proposed project includes a BESS, provide the ITC percentage for the BESS (and reflected in your proposal).
State whether the proposed project has “started construction” under one of the methods described in IRS Notice 2018-59 or Notice 2013-29 (in each case, as modified and clarified by all applicable IRS Notices), as applicable (the “Notice”). If the proposed project also includes a BESS, state whether the BESS has “started construction” under one of the methods described in the Notice. If either of the answers is the project or the BESS has started construction, for each of the proposed project and, if applicable, the BESS, state the start-of-construction method (the physical work test or the five percent (5%) safe harbor) and describe in reasonable detail the extent of the physical work performed or to be performed or safe harbor actions taken or to be taken, in each case under the Notice. If the Notice is replaced, superseded, updated, or otherwise modified by statutory amendments, Treasury regulations, IRS guidance published in rulings, notices or bulletins, or other rules, regulations, or laws applicable to the proposed project or the BESS, as applicable, issued, promulgated, or enacted after issuance of the RFP, then, for the proposed project and, if applicable, the BESS, describe in reasonable detail what actions Bidder/Seller has taken or will take to ensure that the proposed project or the BESS, as applicable, satisfies or will satisfy the new or modified methods for establishing beginning of construction pursuant to the Notice (as modified) or other applicable guidance.
If the proposed project, or if applicable, the BESS, has not “started construction” under one of the methods described in the Notice (as defined above), provide responses to the requests set forth in clauses (a) through (c) below:
Confirm that Bidder is able to cause the construction of the proposed project and, if applicable, the BESS to satisfy the labor requirements described in IRC Section 45(b)(6)-(8), 45Y(g)(9)-(10), 48(a)(9)-(11), 48E(d)(3)-(4) and similar Code sections (collectively, “Tax Credit Labor Requirements”). If Bidder is unable to confirm, provide the rationale.
Confirm that the proposed purchase price reflects the costs Bidder requires to commit to comply with the Tax Credit Labor Requirements and is not subject to adjustment. If Bidder is unable to confirm, provide the rationale.
Provide a statement setting forth (i) the collective value of costs to be included in the purchase price or energy price, as applicable, to comply with the Tax Credit Labor Requirements, (ii) a reasonably detailed line item breakdown of such costs, including, without limitation, (A) the levels of wages paid or to be paid to laborers and mechanics during construction of the proposed project and (B) the percentage of total labor hours performed by qualified apprentices with respect to construction of the proposed project, (iii) the then-most recent levels of prevailing wages paid to laborers and mechanics in the locality in which the proposed project is located as determined by the Secretary of Labor pursuant to the Davis-Bacon Act, and (iv) whether each contractor and subcontractor that employs four or more individuals to perform construction on the proposed project will employ at least one qualified apprentice.
State whether the proposed project will be located in an "energy community" as defined in IRC Section 45(b)(11). If the answer is in the affirmative, explain the rationale for this conclusion, including the type of “energy community.”
State whether the proposed project and, if applicable, the BESS, will satisfy the “domestic content” requirement provided for in IRC Section 45(b)(9)(B), 45Y(g)(11), 48(a)(12), or 48E(a)(3)(B). If the answer is in the affirmative; provide responses to the requests set forth in clauses (a) and (b) below.
Explain the rationale for the conclusion that the project and/or the BESS, as applicable, will satisfy the Domestic Content Requirements, including the percentage of the total cost of the components for the proposed project or the BESS, as applicable, that is assumed in the proposal to be attributable to components mined, produced, or manufactured in the United States, and the process by which Bidder will confirm that steel, iron, and manufactured products meet the Domestic Content Requirements, and
Confirm that the proposed purchase price reflects the costs Bidder requires to satisfy the Domestic Content” Requirements.
Tax Minimization Plan.
Describe all efforts and plans to minimize sales, use, Texas gross receipts, transfer, or similar taxes applicable to the development, engineering, design, procurement, construction (including installation and assembly), commissioning, testing, purchase, or transfer of the Facility and other assets to be acquired by Buyer in a proposed BOT transaction or to the development, engineering, design, procurement, construction (including installation and assembly), commissioning, or testing of or in connection with the Facility in a proposed PPA transaction.
Provide estimates of such taxes applicable to engineering, design, procurement, construction, commissioning, and testing of the Facility. To the extent Bidder’s position is that a sales, use, gross receipts, transfer or similar tax is not applicable to one or more or such activities, explain the basis for such position.
For BOT transactions, provide estimates of such taxes applicable to the transfer of the Facility. If Bidder takes the position that transfer taxes are not applicable to the purchase and transfer of the Facility, explain the basis for such position.
Accounting Certification. Provide the accounting certification described in Appendix D-Attachment E signed by an Accounting Officer (as requested).

## Instructions
Bidders intending to submit a proposal in the RFP must provide a comprehensive response to each question or request set forth in this document. Bidders should respond to any question or request that does not apply to the proposed Facility or transaction with “N/A” or “not applicable”. Bidders must respond to each question by 5:00 pm CPT on the Proposal Submission Deadline. Bidders are required to submit their response to the questions below in such a way that clearly identifies the question to which each response pertains, and then provide the response via PowerAdvocate to the Bid Event Coordinator. Additionally, Bidder should review the terms of the RFP, including all appendices for technical specifications and other guidance or terms regarding the project.

## Sec. 1 - Project Overview
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
1.1 | RFP Details
1.1.1 | Bidder ID
1.1.2 | Resource ID
1.1.3 | Proposal ID
1.2 | Project Details
1.2.1 | Name of Resource
1.2.2 | Location of Resource (County, State)
1.2.3 | Location of Resource (Longitude, Latitude)
1.2.4 | Proposal Type (Acquisition) | PPA's not acceptable
1.2.5 | Guaranteed Project Capacity (BOT transactions) of the BESS Resource
1.2.6 | Guaranteed Substantial Completion Date (BOT)
1.2.7 | MISO or SPP Interconnection Application Queue Number
1.2.8 | Confirm if proposals include NRIS, or ERIS plus NITS
1.2.9 | ERIS Capacity requested in MISO DPP Study
1.2.10 | NRIS Capacity requested in MISO DPP Study
1.2.11 | Please provide a summary of the ownership or any joint ownership of the resource.
1.3 | RFP Compliance
1.3.1 | Confirm the resource is located at a single facility, is AC connected, not being charged by a renewable resource and is not a combined or aggregate resource formed by a "system" of generation resources. | Eligible Resource are resources that are single resources are not and will not be part of a shared facility-type structure or arrangement
1.3.2 | Confirm the selection of the proposed resource is not contingent on selection of another proposed resource. | Eligible Resource are single resources
1.3.3 | Provide a complete redline version of both the Model BOT Agreement and the Scope Book showing all Bidder exceptions to the terms and requirements of either document.
1.4 | Standalone Battery Tolls
1.4.1 | Provide the Seller’s proposed Mechanical Availability for the term of the PPA. If the Mechanical Availability is expected to vary by year, please provide for each year.
1.4.2 | If Mechanical Availability falls below the minimum, what price reduction mechanism does the Seller propose in order to avoid termination?
1.4.3 | Provide the dispatch strategy for the battery, including annual expected energy (P50) output and dispatch profile by hour/ month/ season for the term of the PPA.
1.4.4 | At this time, it is expected that any executed Agreement will have a minimum Mechanical Availability. However, please provide the P90 profile for the battery in order to fully evaluate the proposal.
1.4.5 | Based on the proposed nameplate capacity and dispatch strategy, what capacity guarantee (ZRCs) would the Seller be guaranteeing by season for the MISO Planning Years during the term of the PPA.
1.4.6 | For any capacity shortfalls in the MISO accreditation process, does the Seller agree to use commercially reasonable efforts to buy replacement ZRCs for the Buyer after the initial planning year that ZRCs are awarded for the Planning Resource Auction?
1.4.7 | Is the Seller open to a generation sharing approach where the output of the facility is split 90/10 between the Buyer and Seller?

## Sec. 2 - Bidders Experience
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
2.1 | Relevant Experience
2.1.1 | Please provide a list and summary of all power supply contracts or other off-take agreements that are currently in place or that are expected to be in place anytime in the future (including ancillary services).
2.1.2 | How many utility scale BESS projects (25 MW or greater) has the bidder completed?
2.1.3 | How many BESS projects of equal or greater size to the current proposed resource has the bidder completed?

## Sec. 3 - Project Development
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
3.1 | Engineering
3.1.2 | BESS
3.1.2.1 | Is a Battery Energy Storage System (BESS) included as an option in the proposal? (Yes/No) If yes, please answer questions 3.1.2.2 - 3.1.2.16. If no, proceed to question 3.2
3.1.2.2 | Confirm that the purchase price for the BESS provided in Attachment A DOES NOT INCLUDE any costs of on-going module augmentation (yes/no)
3.1.2.3 | Guaranteed Investment Tax Credit (ITC) - Provide the guaranteed ITC percentage for the BESS (considering the potential impact of the Inflation Reduction Act).
3.1.2.4 | Provide the power rating/capacity of the Battery Energy Storage System (BESS). [MW]
3.1.2.5 | Provide the energy capacity/duration of Battery Energy Storage System (BESS). [MWh]
3.1.2.6 | Provide the annual power rating/capacity degradation assumption (%) over the life of the Battery Energy Storage System (BESS).
3.1.2.7 | Provide the annual energy capacity/duration degradation assumption (%) over the life of the Battery Energy Storage System (BESS).
3.1.2.8 | Consistent with Appendix D - Attachment C (Annual Energy Quantities) for Solar + BESS provide the useful life assumption for the Battery Energy Storage System (BESS). (years)
3.1.2.9 | Consistent with Appendix D- Attachment C (Annual Energy Quantities) for the Solar + BESS and the useful life assumption provided in 3.1.2.9, provide the number of cycles assumed for the BESS.
3.1.2.10 | For the Battery Energy Storage System (BESS), provide the estimated fixed O&M expense that will not change based on energy output of the BESS. The fixed O&M expense estimate should include the following cost components: basic maintenance (checking connections, cleaning equipment, replacing electrical components, etc.) and setting and reconfiguring dispatch schedules. The fixed O&M estimate should not include property taxes or insurance costs, or on-going battery module augmentation costs. ($/kW-yr)
3.1.2.11 | Is the BESS capable of being charged 100% by the resource? (Yes/No)
3.1.2.12 | Proposed Battery Size (MW)
3.1.2.13 | Proposed Battery Duration (Hours)
3.1.2.14 | Confirm the battery has minimum of four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability. | The battery energy storage system must be DC coupled with a minimum four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability.
3.1.2.15 | Confirm Battery Energy Storage System is DC coupled | The battery energy storage system must be DC coupled
3.1.2.16 | Battery Equipment Manufacturer | See Scope Book Appendix 7: Approved Manufacturers
3.1.2.17 | Battery Product Warranty (Years) | Minimum ten (10) years
3.2 | Safety
3.2.1 | Provide safety metrics for the last three (3) years, plus current metrics, for Bidder’s EMR, RIR, and fatalities.
3.2.2 | Is Bidder a registered participant in the Avetta (www.avetta.com) or a comparable third party risk management compliance tracking network or system? If so, please describe the risk management compliance tracking network or system in which Bidder is a registered participant.
3.3 | Project Schedule
3.3.1 | Provide a Level 1 schedule that includes major milestone events and critical activities and associated estimated dates to achieve the successful completion of the project. For purposes of the Level 1 schedule, assume that Buyer’s regulatory approval is received by the date for such approval indicated in the Main Body (as may be updated from time to time, as noted therein). Include those activities in the Project Schedule. Milestones that should be addressed in the schedule include, but are not limited to, the following - Assumed Regulatory Approval/ FNTP, Mobilization to Project Site, Target & Guaranteed Mechanical Completion, Target & Guaranteed Substantial Completion, and Expected Final Completion.
3.4 | Insurance
3.4.1 | Confirm the level of insurance coverage that will be included in the project for the following:
3.4.1.1 | Worker’s compensation | Workers’ Compensation Insurance for statutory obligations imposed by applicable laws
3.4.1.2 | Business auto liability | Policy limits of not less than One Million Dollars ($1,000,000) per accident for bodily injury and property damage
3.4.1.3 | Comprehensive general liability | Policy limits of not less than One Million Dollars ($1,000,000) per occurrence, Two Million Dollars ($2,000,000) aggregate
3.4.1.4 | BOT Only - Errors and omissions | Errors & omissions liability insurance of a design contractor of Seller for the Project shall have policy limits of not less than Five Million Dollars ($5,000,000) per claim and policy aggregate.
3.4.1.5 | BOT Only - Equipment | Equipment Insurance covering Seller’s, Contractors, and Subcontractors materials, tools, equipment, and items used in the performance of the Work (whether owned, rented, or borrowed) that will not become part of the Project
3.4.1.6 | Excess liability insurance | BOT: ExcessLiability Insurance providing for coverage for each occurrence and in the aggregate in excess of the coverage limits of each policy set forth in Section 13.1 of the Model BOT Agreement of not less than the greater of $10,000,000 and ten percent (10%) of the Purchase Price.
3.4.1.7 | BOT Only - Builder’s all risk insurance | Obtain BAR Insurance covering the risk of partial or complete loss or damage to the Workat or prior to the FNTP Date through at least Substantial Completion. Additinoal requirements discussed in Section 13.4 BAR Insruance of Model BOT Agreement
3.6 | Site Hazard Risk
3.6.1.1 | Were Flood (River, Pluvial, Storm Surge) hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
3.6.1.2 | If yes, were Flood (River, Pluvial, Storm Surge) hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Equipment elevation in terms of FEMA Flood Maps and historical water levels
3.6.2.1 | Were Windstorm Hazards Identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
3.6.2.2 | If yes, were Windstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Fastening methods used, tightening methodology, description of wind tunnel testing, etc.
3.6.3.1 | Were Wildfire Hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
3.6.3.2 | If yes, were Wildfire hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Horizontal fire spread characteristics of the chosen panels and required setbacks for Wildfire
3.6.4.1 | Were hailstorm hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
3.6.4.2 | If yes, were hailstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Use of tempered glass panels, safe-stow position, or other ways to mitigate the risk of hail damage.
3.6.5.1 | Were lightning hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
3.6.5.2 | If yes, were lightning hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Lightning protection methodology for all buildings and structures (including solar array equipment)
3.6.6 | What is the planned designed wind speed of the facility (MPH)? | ASCE 7: Risk Category III
3.7 | Site Control and Assessment
3.7.1 | List the real estate and related facilities and real property interests, both owned and leased, with legal description(s), required for development, ownership, use, and/or operation of the resource.
3.7.2 | List all easements, rights-of-way, servitudes, and other land or facility use agreements entered into or required to secure the ability to design, engineer, construct, own, use, and/or operate and maintain the proposed Facility and associated infrastructure.
3.7.3 | Provide an unredacted copy of Bidder’s, Seller’s, or an Affiliate’s proof of ownership of, a legally binding lease of, or a legally binding option or comparable agreement to purchase, lease, or similarly control the site of the proposed resource or any portion thereof.
3.7.4 | For all lease, lease option, or similar site control agreement, identify the term of each agreement, and indicate whether the option includes any option extension rights and the consideration/ payment(s) required for each such extension.
3.7.5 | Provide the acreage secured under each site purchase, lease, or option agreement, the total expected acreage of the project site, and the total expected acreage of the completed project.
3.7.6 | Provide a site map indicating the expected boundary of the full project site, indicating which parcels are currently under Bidder’s control, which are still being negotiated, and which are not due to the owner not being interested in selling/ leasing the land.
3.7.7 | Provide evidence that the project site is properly zoned for the project and the use contemplated by the RFP.
3.7.8 | Provide an executive summary of any formal reports or studies (whether internally or externally prepared or both) related to the risk assessments of the project site, including, without limitation, any risk assessments related to environmental, ecological, archeological, soils, subsurface, geological, hydrogeological, or other site conditions, meteorological conditions, flooding, fire, prior use, habitat, wildlife, or mineral interest or other burdens on title or use that may render the site unusable or delay or otherwise impair or adversely affect project development or use.
3.7.9 | If the site has not been formally assessed for the risks included above, what supporting facts or actions provide assurance that the site is fit for the intended use?
3.7.10 | Indicate what construction-related surveying or testing has been performed at the site and summarize the results or provide executive summaries related to the surveying or testing.
3.7.11 | Is the proposed project site within a floodplain or area subject to storm surge? If so, identify the designated zone and the corresponding level of exposure.
3.7.12 | Is the site located in or near wildfire-susceptible or wildfire-prone areas? If so, please provide the estimated distance from the project site to the nearest edge of each wildfire-susceptible or wildfire-prone area.
3.7.13 | Provide a description of how Bidder plans to mitigate potential wildfire risks to the project, and plans to minimize impacts of any facility fires on forestry, woodlands, grasslands, wildlife, and surrounding property.
3.7.14 | Is the proposed project site subject to windstorms (50-year peak gust) greater than 40 m/s (90 MPH)? If so, provide details of panel fastening system.
3.7.15 | Provide the following details regarding the proposed project site:
3.7.15.1 | A description of the exact location (i.e., street address or latitude and longitude if in a rural location);
3.7.15.2 | A property plat, if available;
3.7.15.3 | Useable acreage required for project size offered;
3.7.15.4 | Other available acreage adjacent to the site;
3.7.15.5 | Nearby acreage directly or indirectly under Bidder’s or Seller’s control;
3.7.15.6 | The land’s primary use(s) over the five years preceding the response to this request (e.g., timber harvesting/forestry, sugar cane production, rice production, farming (noting principal crops), grazing, vacant lot, etc.).
3.7.16 | Provide the following documentation for the proposed site:
3.7.16.1 | Title insurance commitments or policies covering all or any portion of the real property (including appurtenant easements) comprising the proposed site;
3.7.16.2 | ALTA surveys, referencing the above title commitments if available, covering all real property (including appurtenant easements) comprising the proposed site, showing all existing improvements and site features, access to nearest public roads, and plotting all plottable exceptions listed on such title commitments (or noting that such exceptions are either unplottable or do not affect the site);
3.7.16.3 | Copies of the vesting instruments for the proposed site (including appurtenant easements), and all documents listed as exceptions in such title commitments or surveys;
3.7.16.4 | Copies of real property tax documentation; and
3.7.16.5 | Other available real property documentation.
3.7.17 | What LRZ is the project located in MISO?

## Sec. 4 - T&I
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
4.1 | Transmission Interconnection and Full Deliverability
4.1.1 | Is the Bidder electing to self-build all stand-alone network upgrades (SANU), Transmission Owner's Interconnection Facilities (TOIF), and Interconnection Customer Interconnection Facilities (ICIF)? | The TET is responsible for assessing the interconnection, deliverability, and transmission costs and risks associated with proposals received in this RFP
4.1.2 | What is the cost estimate included in the Purchase Price for all SANU, TOIF, and ICIF? | The TET responsibilities will include developing and providing to the RFP Administration Team cost estimates associated with interconnection, deliverability, or transmission upgrades not identified in a Bidder’s proposal or appropriately identified in the proposal but misestimated.
4.1.3 | Confirm that the Bidder will bear all risk associated with construction and arrangement for all transmission interconnection and network upgrades associated with the Facility being fully deliverable to MISO. | All proposals must provide or accept that Bidder is responsible for all costs to obtain the interconnection, deliverability, and transmission service associated with the proposal, including, without limitation, costs associated with transmission interconnection and any network upgrades for the resource.
4.1.4 | Provide a date, which must be at or prior to the proposed Guaranteed Substantial Completion Date, by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Guaranteed Substantial Completion Date.
4.1.5 | Provide a complete copy of the submitted interconnection application(s) for the proposed Facility (including, without limitation, the quantity of NRIS, and ERIS, a copy of either the letter acknowledging the application or, if available, the actual study results related to such application.
4.1.6 | If available, provide a copy of the generator interconnection agreement and any and all related or similar agreements for the resource that have been executed or are material for the resource’s interconnection, deliverability, or transmission capabilities.

## Sec 5. - Environmental
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
5.1 | Environmental Assessment
5.1.1 | Please list any potential environmental impediments to project development, provide documentation and describe the plan to mitigate the impediment.
5.2 | Land/Groundwater
5.2.1 | Has an environmental impact study been conducted for the resource/site? If so, provide a copy of the study(ies). (See also item 3.7.8)
5.2.2 | Does Bidder possess or is Bidder aware of documentation or material identifying or concerning the details of the geological and hydrogeological nature of the soil and groundwater underneath the resource/site? If so, provide (if Bidder possesses or can reasonably obtain) or direct Buyer to the source of (if Bidder does not possess or cannot reasonably obtain) such documentation or material. (See also item 3.7.8)
5.2.3 | Has a wetlands survey/delineation been completed for the proposed project site? Have any potential wetlands been identified on the property? Provide a copy of any completed wetlands surveys/delineations of the property (including desktop reviews and on-site surveys). (See also item 3.7.8)
5.2.4 | Has a wetland delineation been submitted to the United States Army Corps of Engineers for a jurisdictional determination of wetlands on the proposed project site? Provide a copy of any jurisdictional determinations received and requested for the property. (See also item 3.7.8)
5.2.5 | Has the site been evaluated to determine if it is located in a flood hazard area? If so, identify the FEMA flood zone, the corresponding level of exposure and provide a copy of the study.
5.2.6 | If the site is within a 100-year floodplain or flood prone area, provide a detailed flood mitigation plan.
5.3 | Permitting
5.3.1 | Provide a list of all environmental, construction, and operation permits required for the project, including permits needed to develop, design, engineer, build, test, commission, own, use, operate, or maintain the project. Provide a copy of any permits received for the project to date.
5.3.2 | Has the Bidder provided a Phase I ESA? | Bidder must show that a recent “Phase I” or more comprehensive environmental site assessment of the project site has been performed
5.3.2.1 | If Bidder has not provided a Phase I ESA, when is one expected to be available (Month, Year)
5.3.3 | Has Bidder contacted or otherwise been in communication, directly or indirectly, with any of the local governing bodies regarding the proposed project? If so, for each such governing body, indicate whether it has expressed opposition to or support of the project and briefly summarize its position.
5.3.4 | Were any de minimis conditions identified in the project site assessments? If so, describe the condition and any expected effect on the project development or schedule.
5.4 | Noise / Federal Aviation Administration / Department of Defense / Avian / Wetlands / Archeological/Historical Preservation / Protected and Endangered Species
5.4.1 | Has the project site or the Facility been assessed for the applicable requirements, regulations and laws for noise, Federal Aviation Administration, Department of Defense, avian, wetlands, archeological, historical preservation, protected species, and endangered species? If so, state any special concerns or limitations and note whether any regulatory compliance activity has been undertaken by or for the project owner or any Affiliate or submitted to any governmental agency.
5.4.2 | Provide a list of all federally protected wildlife with schedule for obtaining any permits required to operate the develop and operate the Facility.
5.4.3 | Provide a list of all species not considered federally protected, but are considered to be on the watch list to become endangered or federally protected in within the next 5-years?
5.4.4 | Provide the date by which the Bidder guarantees receipt of all permits required to develop and operate the Facility.
5.4.5 | If applicable, what are the anticipated or current controls for noise?
5.4.6 | For each parcel forming the project site, identify the location of the nearest residence.
5.4.7 | For each parcel forming the project site, identify the location of the nearest business.
5.5 | Environmental Compliance
5.5.1 | To the best of Bidder’s knowledge, has the proposed project or the project site been the subject of any complaints or criticism from or concerns expressed by governmental authorities, citizens or citizen groups, business or commercial organizations, or local media regarding environmental matters (including, without limitation, noise, traffic, dust, fishkill, birdkill, riparian matters, planned usage complaints, “Not in My Backyard” complaints, and complaints from nature/sports/ recreation enthusiasts/advocates) or adverse commercial effects?
5.5.2 | Does Bidder/Seller/parent/project owner have (i) an environmental policy or statement of environmental commitment and (ii) an environmental management system that would or may apply to the proposed project or the project site? If so, provide a copy of the policy(ies).
5.5.3 | List any identified known or potential environmental impediments to project development, provide any associated documentation, and describe the plan to mitigate the impediments.
5.5.4 | Has an assessment been made to determine if any material capital expenditures or material expenses need to be incurred to comply with any existing or proposed (whether in preliminary or final form) environmental regulations? If so, describe the assessment and its results.
5.6 | Community Outreach
5.6.1 | Provide Bidder’s plan for community outreach.
5.6.2 | Provide a summary of Bidder’s actions to date with regards to community outreach and/or communication with nearby businesses and residences.
5.6.3 | Provide documentation of any community support or opposition for the proposed project.

## Sec 6. - Financing
Section | Question | RFP Guidance | Response | Document name and location if answer not provided here
6.1 | Credit Support
6.1.1 | Confirm the Bidder has reviewed and is familiar with the RFP's Appendix F - Credit-Collateral Requirements and has provided the Form of Credit Certification | Bidder must include in the Proposal Package the completed Form of Credit Certification (Attachment D of Due Diligence)
6.1.2 | Confirm the Bidder accepts the credit support amounts at each milestone as outlined in Appendix F, and has factored these requirements into the proposal's pricing. | Seller will be required, without exception, to post and maintain credit support as provided in the Model Solar BOT Agreement and Appendix F
6.1.3 | Confirm the Bidder has provided the annual audited financial statements for the past two (2) years and the current year reviewed quarterly financial statements of Bidder (or, if different from Bidder, Seller), if any (the financial statement needs to include the independent auditor’s opinion and notes to the financial statements, the balance sheet, the income statement, and the cash flow statement)
6.2 | ITC
6.2.1 | Does the proposal contemplate the effects of the Investment Tax Credit as specified by the Inflation Reduction Act?
6.2.2 | Provide the ITC percentage for the proposed BESS project.
6.2.3 | Confirm that Bidder is able to cause the construction of the proposed BESS project to satisfy the prevailing wage and apprenticeship requirements described in IRC Section 45(b)(6)-(8), 45Y(g)(9)-(10), 48(a)(9)-(11), 48E(d)(3)-(4) and similar Code sections (collectively, “Tax Credit Labor Requirements”). If Bidder is unable to confirm, provide the rationale.
6.2.4 | Confirm that the proposed purchase price reflects the costs Bidder requires to commit to comply with the Tax Credit Labor Requirements and is not subject to adjustment. If Bidder is unable to confirm, provide the rationale.
6.2.5 | State whether the proposed BESS project is expected to be located in an "energy community" as defined in IRC Section 45(b)(11). If the answer is in the affirmative, explain the rationale for this conclusion, including the type of “energy community,” and whether the project qualifies or intends to qualify for the energy community safe harbor. Also confirm that the proposed purchase price reflects the value of the proposed project locating in an “energy community.”
6.2.6 | State whether the proposed BESS project is expected to satisfy the “domestic content” requirement provided for in IRC Section 45(b)(9)(B), 45Y(g)(11), 48(a)(12), or 48E(a)(3)(B). If the answer is in the affirmative; provide responses to the requests set forth in Sections 6.2.10 and 6.2.11 below.
6.2.7 | Explain the rationale for the conclusion that the proposed BESS project will satisfy the "domestic content" requirement, specifically whether the elective safe harbor for domestic content as provided under IRS Notice 2025-8 (as updated) will be satisifed.
6.2.8 | Confirm that the proposed purchase price reflects the costs Bidder requires to satisfy the "domestic content” requirement, if applicable.
6.3 | Accounting
6.3.1 | Does Bidder's proposal trigger, or is it expected to trigger, long-term liability recognition by EAL, including variable interest entity, derivatives, or capital lease recognition? | EAL will not accept the risk that any long-term liability will or may be recognized on its (or any of its Affiliates’) books in connection with any PPA entered into pursuant to this RFP, whether the long-term liability is due to lease accounting, the accounting for a variable interest entity or derivatives, or any other applicable accounting standard or requirement.
6.3.2 | Confirm the Bidder has provided the Form of Accounting Certification and understands the terms outlined in the signed Accounting Certification. | If requested by ESL, Bidder must include in the Proposal Package the completed Accounting Certification of the Agreement (Attachment D of Due Diligence)
6.4 | Property Tax
6.4.1 | Property Tax:
6.4.1.1 | Please Indicate whether or not the bidder has submitted an application for any property tax abatements, reductions, incentives, or subsidies for the project (Yes/No)
6.4.1.2 | Tax Abatement and Mitigation. Provide any tax abatement, tax reduction, tax deferral, tax mitigation, or similar agreement or arrangement executed by or on behalf of Bidder/Seller or any Affiliate with any federal, state, or local authority or other third party with respect to or affecting the project or the project site, including all amendments to any such agreement and any equipment or services related to the project or the project site. If no such agreement is in place, identify and describe any proposed tax abatement, tax reduction, tax deferral, tax mitigation, or similar arrangement proposed for the project or assumed in the proposed purchase price.
6.4.1.3 | Property Tax Protests. Provide relevant documents related to any formal or informal property tax protests, litigation filed, related correspondence, legal opinions received, and judicial or administrative decisions rendered during the last ten years and year-to-date, and current status of any such proceedings with respect to the project site or the project.
6.4.1.4 | Property Tax Agreements. Provide copies of any formal or informal property tax agreements (i.e., PILOT, TIP, etc.) with state or local authorities in force during the preceding five years or effective in the current year or succeeding years with respect to the project site or the project.
6.4.1.5 | Tax Jurisdictions. List all applicable tax jurisdictions, tax rates, millage rates, assessment ratios, and the current equalization ratio.
6.4.1.6 | Property Tax Abatements. If you answered “yes" to the Property Tax Abatements question 6.4.1.1 please provide critical schedule deadlines and indicate the anticipated likelihood of Bidder/Seller and/or the proposed resource receiving the specified property tax abatements.
6.4.1.7 | For BOT transactions, provide estimates of such taxes applicable to the transfer of the Facility. If Bidder takes the position that transfer taxes are not applicable to the purchase and transfer of the Facility, explain the basis for such position.
6.4.2 | Other Tax Incentives:
6.4.2.1 | Available Tax Benefits. Describe any other awards, grants, incentives, special tax treatment or credits (excluding the federal investment tax credit or production tax credits for solar-powered generation facilities established pursuant to Section 48, Section 48E, Section 45, Section 45Yof the U.S. Internal Revenue Code (“ITC” or “PTC”)), tax abatements (see Section 6.17 for Property Tax Abatements), tax reductions, incentives, or subsidies that are or may be available to the proposed resource or project. Describe the same, identify any applicable critical schedule deadlines, and indicate the anticipated likelihood of Bidder/Seller and/or the proposed resource receiving the same.
6.4.2.2 | Effects if Tax Benefits Not Received. Identify the economic and other effects on the proposed resource or project in the event that any applicable award, grant, incentive, special tax treatment or credit (excluding the ITC or PTC), abatement, reduction, or subsidy is not received.
6.4.3 | Sales and Other Transaction Based Taxes:
6.4.3.1 | Describe all efforts and plans to minimize sales, use, Texas gross receipts, transfer, or similar taxes applicable to the development, engineering, design, procurement, construction (including installation and assembly), commissioning, testing, purchase, or transfer of the Facility and other assets to be acquired by Buyer in a proposed BOT transaction or to the development, engineering, design, procurement, construction (including installation and assembly), commissioning, or testing of or in connection with the Facility in a proposed PPA transaction.
6.4.3.2 | Provide estimates of such taxes applicable to engineering, design, procurement, construction, commissioning, and testing of the Facility. To the extent Bidder’s position is that a sales, use, gross receipts, transfer or similar tax is not applicable to one or more or such activities, explain the basis for such position.
6.5 | Miscellaneous
6.5.1 | Has Bidder provided a plan for the financing of the project?
6.5.2 | Does the Bidder agree to financially settle a the EAL load node | Products will be financially settled at the EAL Load Node.